## Sheet1
Week | Task | Who did what?
1 | Write and post resume | All
| Team style & Career Discussion | All
| Create team name & philosophy | All
| Discuss communication and team meetings | All
| Post home IP Address | All
2 | Create Linux Command note sheet | All
| Create Vim Command note sheet | Alyssa & David I
| Create Agile/Scrum note sheet | Devin & Matt
| Sketch ideas for webpage | Adam
| Meet with product owner and discuss progress | Alyssa & ?
3 | Create github.com acount | All
| Watch Git Basics videos | All
| Create git/github note sheet | Kyle
| Implement team website using bootstrap | Dave Z
| Create Bootstrap note sheet | Alyssa & Matt
| Make all note sheets for consistent look and feel | All
| Revise and review peer resumes | All
| Meet with product owner and discuss progress | Alyssa & Kyle
4 | Create three rempty repositories on github
Clone the repoistory to local account on Linux Server
Link teams remote gitbut repository
Use Vim to modify cloned java programs
Continue developing team web site
5 | Gather all remaining materials
Prepare website and presentation
Present on Friday